## Sprints
ID | Importance (mức độ ưu tiên) | Sprint(Tên giai đoạn ở đây chia theo tuần) | Notes | How to demo | Status | Points
1 | High | Building the User Interface (UI) | Using Basic Controls in Android | AVD (Android Virtual Device) | Opened
2 | High | Adding Functionality to a UI | Using Activity, Creating Menu, Handlers Event Programming | AVD (Android Virtual Device) | Opened
3 | High | Building a Navigation Drawer | Replace the Dashboard Screen | AVD (Android Virtual Device) | Opened
4 | High | Creating UI: Content Detail Layout | Creating Explicit Intent && Attach Data | AVD (Android Virtual Device) | Opened

## Sprint 1 Retrospective example
Team Member | Set the Stage (how did you feel this sprint) | What Happend this sprint (Tuần vừa rồi có những vấn đề gì?) | Why did those things happen (Tại sao ?) | What To Do to keep up what worked well and prevent what didn't (Cách khắc phục)
Dao Tien Tu | Design: creating and customize | Creating dashboard | Not have graphic interface | Customize style + Refer interface other + Adding style
Dao Tien Tu | Design: creating and customize | Creating menu using Button Widget | Not have graphic interface | Customize style + Adding style
Dao Tien Tu | Design: creating and customize | Creating menu using ListView Widget | Not have graphic interface | Customizing
Dao Tien Tu | Design & Events Handling: Building a Navigation Drawer | Not have Dashboard Screen | Not have graphic interface | Remove or create new dashboard screen

## Sprint 1 tasks remaining ex
| Sprint Goal: Complete Sprint 3 stories including stories 32, 33, 36 (18 pts) (Mục tiêu của tuần vừa rồi) |  |  | Planned tasks | 16 | 14.2222 | 12.4444 | 10.6667 | 8.8889 | 7.1111 | 5.3333 | 3.5556 | 1.7778 | 1.7778 | 1.7778 | 1.7778 | 1.7778 | 1.7778
|  |  |  | Tasks remaining | 16 | 16 | 16 | 12 | 12 | 12 | 10 | 9 | 8 | 8 | 8 | 2 | 2 | 2 | 0
Task ID | Task | Assigned to | Status | Date/complete on | 2014-06-16 | 2014-06-20 | 2014-06-23 | 2014-06-27 | 2014-06-30 | 2014-07-04 | 2014-07-11 | 2014-07-14 | 2014-07-18 | 2014-07-21 | 2014-07-25 | 2014-07-28 | 2014-08-01 | 2014-08-04 | 2014-08-08
S01 | Creating, Building User Interface and Handling Events | bar: 2014-08-04 to 2014-08-08
| Creating ListView Widget and Fill Data Example (List Item) | Tu | Done |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Creating a Navigation Drawer (Creating New DashBoard Example) | Tu | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Creating GridView Layout and Fill Data Example | Tu | Done |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Creating content detail layout and push data example through Intent Explicit from ListView (Menu Items) | Tu | Done |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Creating animation effects to switch between layouts | Tu | Done |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S02 | Designing and Connecting to SQLite Database
| Designing Database (Using SQLite Database) | Tu | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Connecting to Database (Using Existing File SQLite Database) | Tu | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fetch Data in Table Article to ListView (Fragment ¦ Activity) | Tu | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Fetch Data in Table Article to GridView (Fragment ¦ Activity) | Tu | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Fetch Data Article Details to WebView in LinearLayout | Tu | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
S03 | Buiding server using PHP & MySQL | bar: 2014-08-04 to 2014-08-08
| Designing and Connecting to MySQL Database | Tu | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Building modules to handle data (CRUD: Create, Read, Update, Delete) | Tu | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Return JSON data from server | Tu | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Android get and parse JSON Data through URL | Tu | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
S04 | Adding stylesheet and customizing UI | bar: 2014-08-04 to 2014-08-08
| Adding stylesheet into WebView (using file styles.css in assets folder) | Tu | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Adding stylesheet for Action Bar, Layout and Form Widgets | Tu | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
[5 empty] | 16 | 16 | 16 | 12 | 12 | 12 | 10 | 9 | 8 | 8 | 8 | 2 | 2 | 2 | 0